## 926 Metrics
926 Totals
Test ID | Seconds | Hrs | OBC Config | HW Config | Running On… | # Iterations | Result | Exec Time (s) | Rack of Success | Passing Results File or Notes | Additional Info
OBCTP12_SUB1.seq | 8640 | 2.4 | MRM¦TIN | ANY |  | 2 | P | 9539 | 103 | OBCTP12_SUB1_Report[4 13 2018][3 58 32 PM][103][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB1.seq"
OBCTP12_SUB2.seq | 5760 | 1.6 | MRM¦TIN | ANY |  | 1 | P | 5891 | 120 | OBCTP12_SUB2_Report[4 16 2018][6 05 09 PM][120][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB2.seq"
OBCTP12_SUB3.seq | 5760 | 1.6 | MRM¦TIN | ANY |  | 4 | P | 5601 | 080 | OBCTP12_SUB3_Report[4 15 2018][10 25 57 AM][080][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB3.seq"
OBCTP12_SUB4.seq | 22320 | 6.2 | MRM¦TIN | ANY |  | 1 | P | 21525 | 083 | OBCTP12_SUB4_Report[4 13 2018][1 22 13 PM][083][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB4.seq"
OBCTP12_SUB5.seq | 22320 | 6.2 | MRM¦TIN | ANY |  | 1 | P | 11244 | 113 | OBCTP12_SUB5_Report[4 13 2018][1 29 33 PM][113][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB5.seq"
OBCTP12_SUB6.seq | 12961 | 3.6003 | MRM¦TIN | ANY |  | 1 | P | 13290 | 075 | OBCTP12_SUB6_Report[4 13 2018][2 14 22 PM][075][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB6.seq"
OBCTP12_SUB8.seq | 6858 | 1.905 | MRM¦TIN | ANY |  | 1 | P | 6860 | 118 | OBCTP12_SUB8_Report[4 13 2018][2 23 03 PM][118][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB8.seq"
OBCTP12_SUB9.seq | 21745 | 6.0403 | MRM¦TIN | ANY |  | 1 | C | 5539 | 080 | OBCTP12_SUB9_Report[4 17 2018][1 08 39 PM][080][F].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0012 (3_6 ITCS Territory Entry Exit)\OBCTP12_SUB9.seq"
OBCTP15_SUB1.seq | 6566 | 1.8239 | MRM¦TIN | ANY |  | 3 | C | 6457 | 105 | OBCTP15_SUB1_Report[4 13 2018][2 47 09 PM][105][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB1.seq"
OBCTP15_SUB2.seq | 8555 | 2.3764 | MRM¦TIN | ANY |  | 7 | C | 9020 | 107 | OBCTP15_SUB2_Report[4 17 2018][10 40 29 AM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB2.seq"
OBCTP15_SUB3.seq | 3431 | 0.95306 | MRM¦TIN | ANY |  | 1 | P | 3743 | 067 | OBCTP15_SUB3_Report[4 13 2018][3 42 43 PM][067][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB3.seq"
OBCTP15_SUB4.seq | 5794 | 1.6094 | MRM¦TIN | ANY |  | 2 | C | 5997 | 086 | OBCTP15_SUB4_Report[4 13 2018][3 53 28 PM][086][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB4.seq"
OBCTP15_SUB5.seq | 15679 | 4.3553 | MRM¦TIN | ANY |  | 4 | C | 15864 | 104 | OBCTP15_SUB5_Report[4 21 2018][2 59 31 PM][086][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB5.seq"
OBCTP15_SUB6.seq | 13900 | 3.8611 | MRM¦TIN | ANY |  | 2 | P | 13414 | 113 | OBCTP15_SUB6_Report[4 13 2018][10 46 19 PM][113][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB6.seq"
OBCTP15_SUB7.seq | 4649 | 1.2914 | MRM¦TIN | ANY |  | 7 | P | 4706 | 075 | OBCTP15_SUB7_Report[4 16 2018][12 56 18 PM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB7.seq"
OBCTP15_SUB8.seq | 11224 | 3.1178 | MRM¦TIN | ANY |  | 2 | P | 11314 | 105 | OBCTP15_SUB8_Report[4 13 2018][9 50 59 PM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB8.seq"
OBCTP15_SUB9.seq | 9823 | 2.7286 | MRM¦TIN | ANY |  | 3 | C | 9491 | 107 | OBCTP15_SUB9_Report[4 15 2018][1 22 31 PM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB9.seq"
OBCTP15_SUB10.seq | 6237 | 1.7325 | MRM¦TIN | ANY |  | 2 | P | 6323 | 083 | OBCTP15_SUB10_Report[4 13 2018][7 23 27 PM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0015 (3_7 Speed Limit Determination)\OBCTP15_SUB10.seq"
OBCTP47_Sub1.seq | 11579 | 3.2164 | MRM¦TIN | ANY |  | 2 | C | 11595 | 080 | OBCTP47_Sub1_Report[4 15 2018][12 00 50 PM][080][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0047 (General Departure Test)\OBCTP47_Sub1.seq"
OBCTP47_SUB3-4.seq | 7637 | 2.1214 | MRM¦TIN | ANY |  | 3 | C | 7719 | 120 | OBCTP47_Sub3-4_Report[4 15 2018][4 00 35 PM][120][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0047 (General Departure Test)\OBCTP47_Sub3-4.seq"
OBCTP56.seq | 13127 | 3.6464 | MRM¦TIN | ANY |  | 1 | P | 12605 | 107 | OBCTP56_Report[4 13 2018][5 44 15 PM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0056 (Target Determination Interact TP)\OBCTP56.seq"
OBCTP56_SUB2.seq | 8612 | 2.3922 | MRM¦TIN | OLD |  | 2 | P | 8781 | 103 | OBCTP56_SUB2_Report[4 13 2018][6 39 04 PM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0056 (Target Determination Interact TP)\OBCTP56_SUB2.seq"
OBCTP56_SUB3.seq | 5350 | 1.4861 | MRM¦TIN | ANY |  | 1 | P | 4943 | 075 | OBCTP56_SUB3_Report[4 13 2018][5 57 05 PM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0056 (Target Determination Interact TP)\OBCTP56_SUB3.seq"
OBCTP56_SUB4.seq | 7914 | 2.1983 | MRM¦TIN | ANY |  | 2 | P |  | 101 | OBCTP56_SUB4_Report[4 20 2018][2 25 00 AM][101][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0056 (Target Determination Interact TP)\OBCTP56_SUB4.seq"
OBCTP56_SUB5.seq | 2158 | 0.59944 | MRM¦TIN | ANY |  | 1 | P | 2280 | 105 | OBCTP56_SUB5_Report[4 13 2018][7 17 43 PM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0056 (Target Determination Interact TP)\OBCTP56_SUB5.seq"
OBCTP57.seq | 12541 | 3.4836 | MRM¦TIN | ANY |  | 2 | P | 12163 | 113 | OBCTP57_Report[4 13 2018][7 22 37 PM][113][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0057 (Targ Determ Targ Type - DTT TP)\OBCTP57.seq"
OBCTP57_SUB2.seq | 9135 | 2.5375 | MRM¦TIN | ANY |  | 3 | P | 9101 | 120 | OBCTP57_SUB2_Report[4 15 2018][1 27 36 PM][120][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0057 (Targ Determ Targ Type - DTT TP)\OBCTP57_SUB2.seq"
OBCTP57_SUB3.seq | 6955 | 1.9319 | MRM¦TIN | ANY |  | 3 | C | 6350 | 120 | OBCTP57_SUB3_Report[4 15 2018][7 31 03 PM][120][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0057 (Targ Determ Targ Type - DTT TP)\OBCTP57_SUB3.seq"
OBCTP58_SUB1.seq | 6827 | 1.8964 | MRM¦TIN | ANY |  | 1 | P | 6421 | 117 | OBCTP58_SUB1_Report[4 13 2018][8 24 45 PM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0058 (Speed Limit Interaction TP)\OBCTP58_SUB1.seq"
OBCTP58_SUB2.seq | 5419 | 1.5053 | MRM¦TIN | ANY |  | 4 | C | 5565 | 077 | OBCTP58_SUB2_Report[4 13 2018][8 33 40 PM][077][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0058 (Speed Limit Interaction TP)\OBCTP58_SUB2.seq"
OBCTP58_SUB3.seq | 7852 | 2.1811 | MRM¦TIN | ANY |  | 2 | C | 7928 | 103 | OBCTP58_SUB3_Report[4 13 2018][9 06 37 PM][103][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0058 (Speed Limit Interaction TP)\OBCTP58_SUB3.seq"
OBCTP58_SUB4.seq | 3955 | 1.0986 | MRM¦TIN | ANY |  | 1 | P | 3727 | 083 | OBCTP58_SUB4_Report[4 13 2018][9 10 06 PM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0058 (Speed Limit Interaction TP)\OBCTP58_SUB4.seq"
OBCTP58_SUB5.seq | 2127 | 0.59083 | MRM¦TIN | ANY |  | 1 | P | 2475 | 107 | OBCTP58_SUB5_Report[4 13 2018][9 15 22 PM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0058 (Speed Limit Interaction TP)\OBCTP58_SUB5.seq"
OBCTP60.seq | 11491 | 3.1919 | MRM¦TIN | ANY |  | 1 | C | 11734 | 080 | OBCTP60_Report[4 13 2018][9 30 42 PM][080][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0060 (Targ Determ Alarm-Brake TP)\OBCTP60.seq"
OBCTP61.seq | 5990 | 1.6639 | MRM¦TIN | OLD |  | 2 | P | 5731 | 077 | OBCTP61_Report[4 14 2018][12 38 16 AM][077][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0061 (Targ Determ Targ Speed TP)\OBCTP61.seq"
OBCTP61_SUB2.seq | 9252 | 2.57 | MRM¦TIN | OLD |  | 1 | P | 7725 | 117 | OBCTP61_SUB2_Report[4 13 2018][10 13 25 PM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0061 (Targ Determ Targ Speed TP)\OBCTP61_SUB2.seq"
OBCTP61_SUB3.seq | 3034 | 0.84278 | MRM¦TIN | OLD |  | 3 | C | 3142 | 107 | OBCTP61_SUB3_Report[4 15 2018][7 35 18 PM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0061 (Targ Determ Targ Speed TP)\OBCTP61_SUB3.seq"
OBCTP61_SUB4.seq | 8246 | 2.2906 | MRM¦TIN | OLD |  | 2 | C | 8070 | 075 | OBCTP61_SUB4_Report[4 15 2018][8 27 29 PM][075][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0061 (Targ Determ Targ Speed TP)\OBCTP61_SUB4.seq"
OBCTP69.seq | 9814 | 2.7261 | MRM¦TIN | ANY |  | 3 | C | 10018 | 077 | OBCTP69_Report[4 15 2018][8 29 48 PM][077][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0069 (Absolute Stop Conditions)\OBCTP69.seq"
OBCTP69_SUB2.seq | 14504 | 4.0289 | MRM¦TIN | ANY |  | 1 | P | 14176 | 083 | OBCTP69_SUB2_Report[4 13 2018][10 13 49 PM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0069 (Absolute Stop Conditions)\OBCTP69_SUB2.seq"
OBCTP71.seq | 18883 | 5.2453 | MRM¦TIN | ANY |  | 5 | P | 18924 | 88] | OBCTP71_Report[4 18 2018][10 46 10 AM][088][P].html\ | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0071 (Home Signals - Speed Through CP TP)\OBCTP71.seq"
OBCTP73.seq | 9012 | 2.5033 | MRM¦TIN | ANY |  | 3 | P | 9114 | 083 | OBCTP73_Report[4 15 2018][8 35 27 PM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0073 (Home Signals - Speed After Signal TP)\OBCTP73.seq"
OBCTP75.seq | 7886 | 2.1906 | MRM¦TIN | ANY |  | 2 | P | 8336 | 103 | OBCTP75_Report[4 15 2018][8 41 22 PM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0075 (Home Signals - Speed At Signal TP)\OBCTP75.seq"
OBCTP77.seq | 793 | 0.22028 | MRM¦TIN | ANY |  | 1 | P | 898 | 105 | OBCTP77_Report[4 14 2018][1 00 33 AM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0077 (OBC Direction Determination TP)\OBCTP77.seq"
OBCTP78.seq | 11761 | 3.2669 | MRM¦TIN | ANY |  | 1 | P | 11545 | 075 | OBCTP78_Report[4 14 2018][12 56 33 AM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0078 (Intermediate Signals TP #1)\OBCTP78.seq"
OBCTP80.seq | 5233 | 1.4536 | MRM¦TIN | OLD |  | 1 | P | 5197 | 105 | OBCTP80_Report[4 14 2018][1 17 51 AM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0080 (Intermediate Signals TP #2)\OBCTP80.seq"
OBCTP80_sub2.seq | 8339 | 2.3164 | MRM¦TIN | OLD |  | 2 | C | 8291 | 105 | OBCTP80_sub2_Report[4 15 2018][8 48 12 PM][105][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0080 (Intermediate Signals TP #2)\OBCTP80_sub2.seq"
OBCTP80_sub3.seq | 5813 | 1.6147 | MRM¦TIN | OLD |  | 1 | P | 5723 | 117 | OBCTP80_sub3_Report[4 14 2018][1 15 01 AM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0080 (Intermediate Signals TP #2)\OBCTP80_sub3.seq"
OBCTP81.seq | 5233 | 1.4536 | MRM¦TIN | ANY |  | 2 | P | 6452 | 117 | OBCTP81_Report[4 14 2018][3 58 13 AM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0081 (OBC Direction Rollback Fault TP)\OBCTP81.seq"
OBCTP89.seq | 7772 | 2.1589 | MRM¦TIN | ANY |  | 1 | P | 7481 | 083 | OBCTP89_Report[4 14 2018][2 13 12 AM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0089 (OBC ITCS Footprint and Location TP)\OBCTP89.seq"
OBCTP91_SUB1.seq | 14443 | 4.0119 | MRM¦TIN | ANY |  | 2 | C | 14355 | 077 | OBCTP91_SUB1_Report[4 14 2018][2 15 12 AM][077][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0091 (OBC Valid-Invalid Train Location TP)\OBCTP91_SUB1.seq"
OBCTP91_SUB2.seq | 6352 | 1.7644 | MRM¦TIN | ANY |  | 2 | C | 4389 | 107 | OBCTP91_SUB2_Report[4 16 2018][12 42 10 AM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0091 (OBC Valid-Invalid Train Location TP)\OBCTP91_SUB2.seq"
OBCTP99.seq | 3132 | 0.87 | MRM¦TIN | ANY |  | 1 | P | 3525 | 105 | OBCTP99_Report[4 14 2018][2 45 26 AM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0099 (Penalty Release TRAIL & YARD TP)\OBCTP99.seq"
OBCTP99_SUB2.seq | 3828 | 1.0633 | MRM¦TIN | ANY |  | 1 | P | 3843 | 117 | OBCTP99_SUB2_Report[4 14 2018][2 52 50 AM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0099 (Penalty Release TRAIL & YARD TP)\OBCTP99_SUB2.seq"
OBCTP99_SUB3.seq | 6835 | 1.8986 | MRM¦TIN | ANY |  | 3 | P | 6770 | 105 | OBCTP99_SUB3_Report[4 14 2018][9 45 27 AM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0099 (Penalty Release TRAIL & YARD TP)\OBCTP99_SUB3.seq"
OBCTP99_SUB4.seq | 7038 | 1.955 | MRM¦TIN | ANY |  | 2 | C | 6968 | 107 | OBCTP99_SUB4_Report[4 15 2018][10 44 08 PM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0099 (Penalty Release TRAIL & YARD TP)\OBCTP99_SUB4.seq"
OBCTP99_SUB5.seq | 6971 | 1.9364 | MRM¦TIN | ANY |  | 1 | P | 6954 | 080 | OBCTP99_SUB5_Report[4 16 2018][7 59 52 AM][080][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0099 (Penalty Release TRAIL & YARD TP)\OBCTP99_SUB5.seq"
OBCTP99_SUB6.seq | 7093 | 1.9703 | MRM¦TIN | ANY |  | 2 | C | 7076 | 103 | OBCTP99_SUB6_Report[4 15 2018][11 01 30 PM][103][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0099 (Penalty Release TRAIL & YARD TP)\OBCTP99_SUB6.seq"
OBCTP102.seq | 8391 | 2.3308 | MRM¦TIN | ANY |  | 10 | C | 7917 | 103 | OBCTP102_Report[4 19 2018][5 50 17 AM][103][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0102 (Database Test TP)\OBCTP102.seq"
OBCTP102_SUB2.seq | 8408 | 2.3356 | MRM¦TIN | ANY |  | 2 | C | 8959 | 083 | OBCTP102_SUB2_Report[4 15 2018][11 08 55 PM][083][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0102 (Database Test TP)\OBCTP102_SUB2.seq"
OBCTP102_SUB4.seq | 10535 | 2.9264 | MRM¦TIN | ANY |  | 1 | P | 11121 | 083 | OBCTP102_SUB4_Report[4 14 2018][4 19 33 AM][083][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0102 (Database Test TP)\OBCTP102_SUB4.seq"
OBCTP102_SUB5.seq | 5705 | 1.5847 | MRM¦TIN | ANY |  | 3 | C | 5641 | 105 | OBCTP102_SUB5_Report[4 14 2018][5 37 44 AM][105][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0102 (Database Test TP)\OBCTP102_SUB5.seq"
OBCTP102_SUB6.seq | 8600 | 2.3889 | MRM¦TIN | ANY |  | 2 | C | 9485 | 107 | OBCTP102_SUB6_Report[4 16 2018][6 09 30 PM][107][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0102 (Database Test TP)\OBCTP102_SUB6.seq"
OBCTP102_SUB7.seq | 3765 | 1.0458 | MRM¦TIN | ANY |  | 3 | P | 4151 | 103 | OBCTP102_SUB7_Report[4 17 2018][9 05 53 PM][103][P].html
OBCTP102_SUB8.seq | 2747 | 0.76306 | MRM¦TIN | ANY |  | 2 | C | 2612 | 105 | OBCTP102_SUB8_Report[4 19 2018][9 07 58 AM][105][F].html
OBCTP108.seq | 9694 | 2.6928 | MRM¦TIN | ANY |  | 2 | P | 9292 | 104 | OBCTP108_Report[4 17 2018][10 42 35 PM][104][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0108 (Predictive Braking 2 TP)\OBCTP108.seq"
OBCTP108_Sub2.seq (Rev logs Enabled required) | 4663 | 1.2953 | MRM¦TIN | ANY |  | 2 | P | 4312 | 107 | OBCTP108_Sub2_Report[4 18 2018][9 47 27 AM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0108 (Predictive Braking 2 TP)\OBCTP108_Sub2.seq"
OBCTP110.seq | 10418 | 2.8939 | MRM¦TIN | ANY |  | 2 | P | 10260 | 120 | OBCTP110_Report[4 16 2018][9 53 19 PM][120][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0110 (Predictive Braking 1 TP)\OBCTP110.seq"
OBCTP110_Sub2.seq | 3612 | 1.0033 | MRM¦TIN | ANY |  | 1 | P | 3921 | 103 | OBCTP110_Sub2_Report[4 14 2018][6 09 50 AM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0110 (Predictive Braking 1 TP)\OBCTP110_Sub2.seq"
OBCTP115.seq | 12772 | 3.5478 | MRM¦TIN | ANY |  | 2 | C | 12902 | 083 | OBCTP115_Report[4 16 2018][5 46 02 AM][083][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0115 (Predictive Braking 3 TP)\OBCTP115.seq"
OBCTP128_Sub1.seq | 7118 | 1.9772 | MRM¦TIN | ANY |  | 2 | P | 7285 | 103 | OBCTP128_Sub1_Report[4 14 2018][9 58 43 AM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0128 (Targetless Braking Enforcement TP1)\OBCTP128_Sub1.seq"
OBCTP128_Sub2.seq | 9200 | 2.5556 | MRM¦TIN | ANY |  | 1 | P | 9097 | 105 | OBCTP128_Sub2_Report[4 14 2018][7 12 46 AM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0128 (Targetless Braking Enforcement TP1)\OBCTP128_Sub2.seq"
OBCTP128_Sub3.seq | 3072 | 0.85333 | MRM¦TIN | ANY |  | 1 | P | 2875 | 103 | OBCTP128_Sub3_Report[4 14 2018][7 17 10 AM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0128 (Targetless Braking Enforcement TP1)\OBCTP128_Sub3.seq"
OBCTP131_SUB1.seq | 5709 | 1.5858 | MRM¦TIN | ANY |  | 2 | P | 5572 | 075 | OBCTP131_SUB1_Report[4 16 2018][12 40 37 AM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0131 (Targetless Braking Enforcement TP4)\OBCTP131_SUB1.seq"
OBCTP131_SUB2.seq | 5967 | 1.6575 | MRM¦TIN | ANY |  | 4 | C | 6374 | 077 | OBCTP131_SUB2_Report[4 16 2018][12 54 16 AM][077][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0131 (Targetless Braking Enforcement TP4)\OBCTP131_SUB2.seq"
OBCTP132.seq | 6489 | 1.8025 | MRM¦TIN | ANY |  | 2 | C | 6617 | 103 | OBCTP132_Report[4 14 2018][8 07 16 AM][103][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0132 (Predictive Braking 4 TP)\OBCTP132.seq"
OBCTP133.seq | 9178 | 2.5494 | MRM¦TIN | ANY |  | 1 | P | 9590 | 117 | OBCTP133_Report[4 14 2018][8 28 18 AM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0133 (Penalty Release in IN Mode TP)\OBCTP133.seq"
OBCTP133_SUB2.seq | 1540 | 0.42778 | MRM¦TIN | ANY |  | 1 | P | 746 | 075 | OBCTP133_SUB2_Report[4 14 2018][8 34 15 AM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0133 (Penalty Release in IN Mode TP)\OBCTP133_SUB2.seq"
OBCTP133_SUB3.seq | 9433 | 2.6203 | MRM¦TIN | ANY |  | 4 | C | 9062 | 083 | OBCTP133_SUB3_Report[4 16 2018][1 40 42 AM][083][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0133 (Penalty Release in IN Mode TP)\OBCTP133_SUB3.seq"
OBCTP133_SUB4.seq | 4405 | 1.2236 | MRM¦TIN | ANY |  | 1 | P | 4499 | 083 | OBCTP133_SUB4_Report[4 14 2018][9 10 33 AM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0133 (Penalty Release in IN Mode TP)\OBCTP133_SUB4.seq"
OBCTP134.seq | 9795 | 2.7208 | MRM¦TIN | ANY |  | 3 | C | 9518 | 107 | OBCTP134_Report[4 16 2018][1 56 22 AM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0134 (Targetless Braking Enforcement TP2)\OBCTP134.seq"
OBCTP134_SUB2.seq | 8901 | 2.4725 | MRM¦TIN | ANY |  | 1 | P | 8731 | 077 | OBCTP134_SUB2_Report[4 14 2018][9 44 19 AM][077][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0134 (Targetless Braking Enforcement TP2)\OBCTP134_SUB2.seq"
OBCTP134_SUB3.seq | 7210 | 2.0028 | MRM¦TIN | ANY |  | 1 | P | 7490 | 086 | OBCTP134_SUB3_Report[4 14 2018][9 47 17 AM][086][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0134 (Targetless Braking Enforcement TP2)\OBCTP134_SUB3.seq"
OBCTP135.seq | 9444 | 2.6233 | MRM¦TIN | ANY |  | 4 | P | 8606 | 107 | OBCTP135_Report[4 19 2018][4 36 24 AM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0135 (Targetless Braking Enforcement TP3)\OBCTP135.seq"
OBCTP136.seq | 950 | 0.26389 | MRM¦TIN | ANY |  | 1 | P | 1152 | 117 | OBCTP136_Report[4 14 2018][11 09 34 AM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0136 (Targetless Braking Enforcement TP5)\OBCTP136.seq"
OBCTP140.seq | 9297 | 2.5825 | MRM¦TIN | ANY |  | 2 | C | 9170 | 077 | OBCTP140_Report[4 16 2018][2 42 39 AM][077][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0140 (Home Signals General TP)\OBCTP140.seq"
OBCTP141.seq | 11613 | 3.2258 | MRM¦TIN | ANY |  | 2 | C | 11547 | 080 | OBCTP141_Report[4 16 2018][2 52 02 AM][080][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0141 (Intermediate Signals General TP)\OBCTP141.seq"
OBCTP142.seq | 11805 | 3.2792 | MRM¦TIN | ANY |  | 1 | P | 11081 | 105 | OBCTP142_Report[4 14 2018][11 39 19 AM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0142 (Restricted Speed Condition for HOS & Occupied OS TP)\OBCTP142.seq"
OBCTP143.seq | 9832 | 2.7311 | MRM¦TIN | ANY |  | 4 | C | 10059 | 117 | OBCTP143_Report[4 17 2018][3 46 49 AM][117][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0143 (Targetless Braking Enforcement TP6)\OBCTP143.seq"
OBCTP144.seq | 5446 | 1.5128 | MRM¦TIN | ANY |  | 2 | C | 5393 | 075 | OBCTP144_Report[4 16 2018][3 45 24 AM][075][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0144 (Invalid TOI and Restricted SSL TP)\OBCTP144.seq"
OBCTP149_SUB1.seq | 3441 | 0.95583 | MRM¦TIN | ANY |  | 1 | P | 4024 | 077 | OBCTP149_SUB1_Report[4 14 2018][12 10 55 PM][077][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0149 (Next Signal Display TP)\OBCTP149_SUB1.seq"
OBCTP149_SUB2.seq | 8100 | 2.25 | MRM¦TIN | ANY |  | 1 | P | 8489 | 083 | OBCTP149_SUB2_Report[4 14 2018][12 14 06 PM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0149 (Next Signal Display TP)\OBCTP149_SUB2.seq"
OBCTP151.seq | 8637 | 2.3992 | MRM¦TIN | OLD |  | 1 | P | 8620 | 103 | OBCTP151_Report[4 14 2018][1 38 33 PM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0151 (Crossing TP1)\OBCTP151.seq"
OBCTP151_SUB2.seq | 5748 | 1.5967 | MRM¦TIN | OLD |  | 3 | C | 5809 | 107 | OBCTP151_SUB2_Report[4 16 2018][4 37 07 AM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0151 (Crossing TP1)\OBCTP151_SUB2.seq"
OBCTP151_SUB3.seq | 6128 | 1.7022 | MRM¦TIN | OLD |  | 4 | C | 6028 | 105 | OBCTP151_SUB3_Report[4 14 2018][8 18 00 PM][105][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0151 (Crossing TP1)\OBCTP151_SUB3.seq"
OBCTP151_SUB4.seq | 3132 | 0.87 | MRM¦TIN | OLD |  | 1 | P | 3544 | 075 | OBCTP151_SUB4_Report[4 14 2018][2 37 53 PM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0151 (Crossing TP1)\OBCTP151_SUB4.seq"
OBCTP152.seq | 5216 | 1.4489 | MRM¦TIN | ANY |  | 2 | P | 5268 | 117 | OBCTP152_Report[4 14 2018][5 01 50 PM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0152 (Crossing TP2)\OBCTP152.seq"
OBCTP152_SUB2.seq | 3067 | 0.85194 | MRM¦TIN | ANY |  | 1 | P | 3148 | 086 | OBCTP152_SUB2_Report[4 14 2018][2 37 46 PM][086][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0152 (Crossing TP2)\OBCTP152_SUB2.seq"
OBCTP152_SUB3.seq | 5230 | 1.4528 | MRM¦TIN | ANY |  | 1 | P | 5248 | 107 | OBCTP152_SUB3_Report[4 16 2018][9 10 47 AM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0152 (Crossing TP2)\OBCTP152_SUB3.seq"
OBCTP152_SUB4.seq | 11819 | 3.2831 | MRM¦TIN | OLD |  | 1 | P | 9206 | 075 | OBCTP152_SUB4_Report[4 14 2018][3 37 52 PM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0152 (Crossing TP2)\OBCTP152_SUB4.seq"
OBCTP153.seq | 12477 | 3.4658 | MRM¦TIN | OLD |  | 1 | P | 12392 | 103 | OBCTP153_Report[4 14 2018][4 03 14 PM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0153 (Crossing TP3)\OBCTP153.seq"
OBCTP153_SUB2.seq | 4410 | 1.225 | MRM¦TIN | ANY |  | 1 | P | 4379 | 086 | OBCTP153_SUB2_Report[4 14 2018][3 31 25 PM][086][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0153 (Crossing TP3)\OBCTP153_SUB2.seq"
OBCTP153_SUB3.seq | 9629 | 2.6747 | MRM¦TIN | ANY |  | 1 | P | 9594 | 105 | OBCTP153_SUB3_Report[4 14 2018][4 13 43 PM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0153 (Crossing TP3)\OBCTP153_SUB3.seq"
OBCTP153_SUB4.seq | 8924 | 2.4789 | MRM¦TIN | ANY |  | 2 | P | 5593 | 107 | OBCTP153_SUB4_Report[4 14 2018][8 37 02 PM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0153 (Crossing TP3)\OBCTP153_SUB4.seq"
OBCTP154.seq | 10715 | 2.9764 | MRM¦TIN | OLD |  | 2 | P | 10785 | 120 | OBCTP154_Report[4 17 2018][9 27 06 PM][120][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0154 (Crossing TP4)\OBCTP154.seq"
OBCTP154_SUB2.seq | 9636 | 2.6767 | MRM¦TIN | OLD |  | 4 | P | 8583 | 107 | OBCTP154_SUB2_Report[4 17 2018][8 15 51 AM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0154 (Crossing TP4)\OBCTP154_SUB2.seq"
OBCTP154_SUB3.seq | 5115 | 1.4208 | MRM¦TIN | OLD |  | 1 | P | 4939 | 117 | OBCTP154_SUB3_Report[4 14 2018][6 31 19 PM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0154 (Crossing TP4)\OBCTP154_SUB3.seq"
OBCTP155.seq | 5426 | 1.5072 | MRM¦TIN | OLD |  | 2 | C | 4941 | 105 | OBCTP155_Report[4 14 2018][6 54 38 PM][105][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0155 (Crossing TP5)\OBCTP155.seq"
OBCTP156.seq | 8063 | 2.2397 | MRM¦TIN | ANY |  | 1 | P | 7993 | 086 | OBCTP156_Report[4 14 2018][4 45 38 PM][086][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0156 (Signal Adoption Test Procedure)\OBCTP156.seq"
OBCTP162.seq | 9488 | 2.6356 | MRM¦TIN | OLD |  | 1 | P | 9506 | 103 | OBCTP162_Report[4 14 2018][7 30 47 PM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0162 (Track Number Determination TP1)\OBCTP162.seq"
OBCTP163.seq | 5312 | 1.4756 | MRM¦TIN | OLD |  | 1 | P | 5025 | 117 | OBCTP163_Report[4 14 2018][7 55 04 PM][117][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0163 (Track Number Determination TP2)\OBCTP163.seq"
OBCTP164.seq | 8616 | 2.3933 | MRM¦TIN | ANY |  | 2 | C | 8498 | 075 | OBCTP164_Report[4 16 2018][5 16 34 AM][075][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0164 (Track Number Determination TP3)\OBCTP164.seq"
OBCTP166.seq | 14420 | 4.0056 | MRM¦TIN | ANY |  | 1 | P | 9587 | 086 | OBCTP166_Report[4 14 2018][7 00 13 PM][086][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0166 (Track Number Determination TP4)\OBCTP166.seq"
OBCTP166_SUB2.seq | 4514 | 1.2539 | MRM¦TIN | ANY |  | 1 | P | 4942 | 083 | OBCTP166_SUB2_Report[4 14 2018][7 30 36 PM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0166 (Track Number Determination TP4)\OBCTP166_SUB2.seq"
OBCTP167.seq | 14250 | 3.9583 | MRM¦TIN | ANY |  | 2 | C | 14965 | 077 | OBCTP167_Report[4 14 2018][8 13 30 PM][077][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0167 (Track Number Determination TP5)\OBCTP167.seq"
OBCTP168.seq | 10550 | 2.9306 | MRM¦TIN | OLD |  | 2 | C | 10454 | 107 | OBCTP168_Report[4 16 2018][6 15 11 AM][107][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0168 (Track Number Determination TP6)\OBCTP168.seq"
OBCTP168_SUB2.seq | 6985 | 1.9403 | MRM¦TIN | ANY |  | 3 | C | 7647 | 120 | OBCTP168_SUB2_Report[4 18 2018][10 43 11 AM][120][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0168 (Track Number Determination TP6)\OBCTP168_SUB2.seq"
OBCTP169.seq | 4615 | 1.2819 | MRM¦TIN | OLD |  | 1 | P | 4873 | 113 | OBCTP169_Report[4 14 2018][8 42 07 PM][113][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0169 (Database Spur TP)\OBCTP169.seq"
OBCTP170.seq | 10509 | 2.9192 | MRM¦TIN | OLD |  | 1 | P | 10120 | 075 | OBCTP170_Report[4 14 2018][8 49 31 PM][075][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0170 (Track Number Determination TP7)\OBCTP170.seq"
OBCTP175.seq | 6691 | 1.8586 | MRM¦TIN | ANY |  | 2 | P | 6120 | 105 | OBCTP175_Report[4 16 2018][9 26 43 AM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0175 (Track Number Determination TP8)\OBCTP175.seq"
OBCTP191.seq | 5270 | 1.4639 | MRM¦TIN | ANY |  | 2 | C | 5324 | 117 | OBCTP191_Report[4 16 2018][9 48 00 AM][117][F].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0191 (MTIE Procedure TP1)\OBCTP191.seq"
OBCTP191_Sub2.seq | 3081 | 0.85583 | MRM¦TIN | ANY |  | 1 | P | 3241 | 086 | OBCTP191_Sub2_Report[4 14 2018][9 41 12 PM][086][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0191 (MTIE Procedure TP1)\OBCTP191_Sub2.seq"
OBCTP192.seq | 7058 | 1.9606 | MRM¦TIN | ANY |  | 2 | P | 7119 | 077 | OBCTP192_Report[4 16 2018][10 49 59 AM][077][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0192 (MTIE Entered and Verified TP)\OBCTP192.seq"
OBCTP192_SUB2.seq | 6500 | 1.8056 | MRM¦TIN | ANY |  | 2 | P | 9361 | 105 | OBCTP192_SUB2_Report[4 15 2018][1 30 42 AM][105][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0192 (MTIE Entered and Verified TP)\OBCTP192_SUB2.seq"
OBCTP193.seq | 7459 | 2.0719 | MRM¦TIN | ANY |  | 2 | C | 7592 | 105 | OBCTP193_Report[4 16 2018][11 09 52 AM][105][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0193 (MTIE Footprint and Location TP)\OBCTP193.seq"
OBCTP193_SUB2.seq | 7713 | 2.1425 | MRM¦TIN | ANY |  | 1 | C | 7637 | 103 | OBCTP193_SUB2_Report[4 14 2018][10 10 11 PM][103][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0193 (MTIE Footprint and Location TP)\OBCTP193_SUB2.seq"
OBCTP193_SUB3.seq | 4509 | 1.2525 | MRM¦TIN | ANY |  | 9 | C | 4607 | 075 | OBCTP193_SUB3_Report[4 16 2018][11 38 25 AM][075][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0193 (MTIE Footprint and Location TP)\OBCTP193_SUB3.seq"
OBCTP193_SUB4.seq | 4548 | 1.2633 | MRM¦TIN | ANY |  | 2 | C | 4415 | 117 | OBCTP193_SUB4_Report[4 16 2018][11 18 10 AM][117][F].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0193 (MTIE Footprint and Location TP)\OBCTP193_SUB4.seq"
OBCTP194.seq | 5819 | 1.6164 | MRM¦TIN | ANY |  | 1 | P | 5726 | 086 | OBCTP194_Report[4 14 2018][10 43 46 PM][086][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0194 (Procedure Selection Menu TP)\OBCTP194.seq"
OBCTP195.seq | 11708 | 3.2522 | MRM¦TIN | ANY |  | 2 | P | 10764 | 083 | OBCTP195_Report[4 15 2018][3 56 32 AM][083][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0195 (MTIE Procedure TP2)\OBCTP195.seq"
OBCTP195_SUB2.seq | 3605 | 1.0014 | MRM¦TIN | ANY |  | 1 | P | 2982 | 080 | OBCTP195_SUB2_Report[4 14 2018][11 18 08 PM][080][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0195 (MTIE Procedure TP2)\OBCTP195_SUB2.seq"
OBCTP196.seq | 7771 | 2.1586 | MRM¦TIN | ANY |  | 1 | P | 6351 | 075 | OBCTP196_Report[4 14 2018][11 39 18 PM][075][P].html | ADD | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0196 (MTIE Procedure TP3)\OBCTP196.seq"
OBCTP216_SUB1.seq | 5685 | 1.5792 | MRM¦TIN | ANY |  | 1 | P | 5567 | 105 | OBCTP216_SUB1_Report[4 14 2018][11 56 56 PM][105][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0216 (Crossing Phase 2 TP)\OBCTP216_SUB1.seq"
OBCTP216_SUB2.seq | 5561 | 1.5447 | MRM¦TIN | ANY |  | 3 | C | 5587 | 117 | OBCTP216_SUB2_Report[4 17 2018][2 12 12 AM][117][F].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0216 (Crossing Phase 2 TP)\OBCTP216_SUB2.seq"
OBCTP216_SUB3.seq | 6628 | 1.8411 | MRM¦TIN | ANY |  | 1 | P | 6146 | 120 | OBCTP216_SUB3_Report[4 15 2018][12 02 25 AM][120][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0216 (Crossing Phase 2 TP)\OBCTP216_SUB3.seq"
OBCTP216_SUB4.seq | 5690 | 1.5806 | MRM¦TIN | ANY |  | 1 | P | 5196 | 080 | OBCTP216_SUB4_Report[4 15 2018][12 17 38 AM][080][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0216 (Crossing Phase 2 TP)\OBCTP216_SUB4.seq"
OBCTP216_SUB5.seq | 7147 | 1.9853 | MRM¦TIN | ANY |  | 1 | P | 7286 | 086 | OBCTP216_SUB5_Report[4 15 2018][12 20 26 AM][086][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\Subsystem Level\OBC Subsystem\Tests\OBCTP0216 (Crossing Phase 2 TP)\OBCTP216_SUB5.seq"
ITCSMichigan_Sub1.seq | 6310 | 1.7528 | MRM¦TIN | ANY |  | 2 | P | 6418 | 103 | ITCSMichigan_Sub1_Report[4 16 2018][12 26 54 PM][103][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\System Level\Amtrak\EndToEnd_DBChecker\ITCSMichigan_Sub1.seq"
ITCSMichigan_Sub2.seq | 6886 | 1.9128 | MRM¦TIN | ANY |  | 1 | P | 7146 | 107 | ITCSMichigan_Sub2_Report[4 15 2018][12 27 14 AM][107][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\System Level\Amtrak\EndToEnd_DBChecker\ITCSMichigan_Sub2.seq"
ITCSMichigan_Sub3.seq | 7119 | 1.9775 | MRM¦TIN | ANY |  | 2 | P | 7602 | 120 | ITCSMichigan_Sub3_Report[4 15 2018][6 57 10 AM][120][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\System Level\Amtrak\EndToEnd_DBChecker\ITCSMichigan_Sub3.seq"
ITCSMichigan_Sub4.seq | 8259 | 2.2942 | MRM¦TIN | ANY |  | 1 | P | 8325 | 083 | ITCSMichigan_Sub4_Report[4 15 2018][1 36 13 AM][083][P].html | CORE | call RunSeq.bat "C:\SCM\VEG\ITCS\System Level\Amtrak\EndToEnd_DBChecker\ITCSMichigan_Sub4.seq"
ITCSUPIllinois.seq | 9412 | 2.6144 | MRM¦TIN | ANY |  | 1 | P | 9434 | 103 | ITCSUPIllinois_Report[4 15 2018][1 38 27 AM][103][P].html | PLUS | call RunSeq.bat "C:\SCM\VEG\ITCS\System Level\UP\EndToEnd_DBChecker\ITCSUPIllinois.seq"
[9 empty] | 142 | Tests to Be executed in Sweep
[9 empty] | 95 | Pass
[9 empty] | 47 | C-Pass
[9 empty] | 142 | Credit Taken For…
[9 empty] | 0 | Needs Analysis (Investigations)
[9 empty] | 100% | % Complete With Passing Results
[9 empty] | 100% | % Complete either Passing/C-Pass/Fail or Investigation
[9 empty] | 309.0203 | Executable Hrs. In sweep - Total
[9 empty] | 295.3031 | Earned Hrs. – Actual completed
[9 empty] | 0 | Tests Failure tied to SW CRs
[9 empty] | 0 | Skipped Tests